## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME: Seasonal Production Demand Forecaster | PROJECT MANAGERS: Nick Sheft & Katherine Barney
PROJECT DELIVERABLE(S): ◦Forecast product demand across different retail categories using historical sales and external seasonal data. ◦Identify key drivers of demand fluctuations (e.g., holidays, promotions, weather, regional factors). ◦Develop predictive models to improve forecasting accuracy. ◦Quantify uncertainty and provide actionable insights for inventory and supply-chain decisions.
SCOPE STATEMENT: The data will include historical sales, holidays, store metadata, weather, region-level data, etc. which will be modeled with time series forecasting. It will utilize big data tools like PySpark with SQL integration.
START DATE | END DATE | OVERALL PROGRESS
2025-09-24 | 12/08/0000 | 0%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Acquire Datasets and Define Project Scope | Katherine & Nick | 2025-09-24 | 2025-10-26 | 32 | Complete
Data Cleaning and Preprocessing | Katherine & Nick | 2025-10-26 | 2025-10-30 | 4 | Complete
Feature Engineering | Katherine & Nick | 2025-10-26 | 2025-10-30 | 4 | Complete
Exploratory Analysis and Vizualizations | Nick |  |  |  | In Progress
Identify Demand Patterns and Correlations | Katherine |  |  |  | In Progress
Data Splitting for Testing and Training | Nick |  |  |  | Not Started
Baseline Model Development | Katherine & Nick |  |  |  | Not Started
Feature Selection | Katherine |  |  |  | Not Started
Predictive Model Engineering | Katherine & Nick |  |  |  | Not Started
Model Evaluation | Nick |  |  |  | Not Started
Uncertainty Quantification | Katherine |  |  |  | Not Started
Scenario Testing | Katherine & Nick |  |  |  | Not Started
Reports and Suggestions Based on Findings | Katherine & Nick |  |  |  | Not Started
Present Findings | Katherine & Nick | 2025-11-30 | 2025-12-08 |  | Not Started